## Sheet1
Tasks | Month - Feb 2020 |  |  |  | Month - Mar 2020 |  |  |  | Month - Apr 2020 |  |  |  | Month - May 2020
Exploratory Data Analysis 1. Statistical Summary 2. Univariate Analysis 3. Bivariate Analysis | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Data pre-processing 1. Oulier Detection and Missing Values 2. Feature Encoding and Scaling 3. Handling Imbalance 4. Feature Selection | bar: Month - Feb 2020 Week 2 to Month - Feb 2020 Week 3
Model Training 1. Building 6 ML models 2. Analysis of the various combinations of pre-processing techniques. | bar: Month - Feb 2020 Week 4 to Month - Mar 2020 Week 6
Model Evaluation 1. Evaluating the model performance of these 6 models 2. Comparative analysis to take out the best ones. | bar: Month - Mar 2020 Week 7 to Month - Mar 2020 Week 8
Hyper-parameter Optimization 1. Running two optimization techniques on the best models 2. Analysis of these methods to get the optimal parameters. | bar: Month - Apr 2020 Week 9 to Month - Apr 2020 Week 10
Model Validation 1. Testing the tuned models on the unseen data. 2. Comparative analysis through various evaluation metrics. | bar: Month - Apr 2020 Week 11 to Month - Apr 2020 Week 12
Thesis Writing 1. Literature review and challenges 2. Proposed Method 3. Results and analysis | bar: Month - May 2020 Week 13 to Month - May 2020 Week 16